Graceful

Open Issue Dependency Graph — Sprints 1–4

Source: GitHub — Jam3sl1u/Graceful (Issues, live as of document generation)

Generated for personal project records

## Scope & Method

This document covers every currently OPEN GitHub issue labeled sprint-1 through sprint-4 in the Graceful repository — 60 issues in total (#24–#83). Sprint 0 (foundation: project init, schema migrations, auth, RLS — issues #10–#23) is fully closed and is not graphed, but is noted where an open issue's original dependency pointed to it.

Each issue in the repo carries a structured "Dependencies" section in its body (Blocked by / Blocks, referencing issue numbers). This document parses those declarations directly — it does not infer dependencies from titles or guesswork. If the repo's issue bodies are incomplete or out of date, this graph will inherit that.

"Blocked by (open)" in the tables below lists only blockers that are themselves still open. An issue with no open blockers is marked "Ready to start."

## Summary

| Sprint | Open issues | High | Med | Low |
| --- | --- | --- | --- | --- |
| Sprint 1 | 10 | 6 | 4 | 0 |
| Sprint 2 | 19 | 14 | 5 | 0 |
| Sprint 3 | 14 | 9 | 4 | 1 |
| Sprint 4 | 17 | 13 | 4 | 0 |
| Total | 60 | 42 | 17 | 1 |

## Ready to Start Now (no open blockers)

12 of 60 open issues have every blocker already closed and can be picked up immediately:

- #24 [Sprint 1] Implement church group creation

- #29 [Sprint 1] Build audit log writer utility + read endpoint (BR-13)

- #37 [Sprint 2] Implement service week CRUD

- #53 [Sprint 3] Implement song catalog CRUD + search (BR-09 key validation)

- #61 [Sprint 3] Implement Google Calendar OAuth connect/disconnect

- #67 [Sprint 4] Integrate Pingram SMS dispatch + webhook verification

- #68 [Sprint 4] Integrate Resend email dispatch + webhook verification

- #70 [Sprint 4] Implement notification preferences (BR-14 minimum-channel guard)

- #75 [Sprint 4] Implement PWA manifest & install prompt

- #76 [Sprint 4] Implement rate limiting on auth, SMS, and write endpoints

- #77 [Sprint 4] Audit input validation (Zod) across all Phase 1 routes

- #78 [Sprint 4] Run infrastructure security pass (HTTPS, CSP, secret scan)

## Key Bottleneck Issues (block the most other open work)

- #37 — Implement service week CRUD  (blocks 5 other open issues)

- #40 — Implement send set invitation (BR-05 double-booking check)  (blocks 5 other open issues)

- #34 — Implement availability set/get  (blocks 3 other open issues)

- #53 — Implement song catalog CRUD + search (BR-09 key validation)  (blocks 3 other open issues)

- #59 — Implement event CRUD (BR-10 time validation)  (blocks 3 other open issues)

- #24 — Implement church group creation  (blocks 2 other open issues)

- #25 — Implement join church group via invite code  (blocks 2 other open issues)

- #26 — Build member directory endpoint  (blocks 2 other open issues)

# Cross-Sprint Dependency Overview

Only dependencies that cross a sprint boundary are drawn here, to keep the chain of custody between sprints readable. Full within-sprint detail follows in the per-sprint sections.

# Sprint 1 — Foundation

Church group, members, roles, instruments

Legend:    Box = feature issue   |   Note shape = chore issue (tests, infra, audits)   |   Red fill = priority:high   Orange fill = priority:med   Green fill = priority:low   |   Grey dashed box = closed Sprint 0 prerequisite (already satisfied)

## Sprint 1 — Foundation — Issue Detail

| # | Title | Priority | Blocked by (open) | Blocks | Status |
| --- | --- | --- | --- | --- | --- |
| 24 | Implement church group creation | HIGH | — | #25, #26 | Ready to start |
| 25 | Implement join church group via invite code | HIGH | #24 | #30, #26 | Blocked |
| 26 | Build member directory endpoint | MED | #24 | #27, #28 | Blocked |
| 27 | Implement role assignment & multi-admin support (BR-03, BR-04, BR-12) | HIGH | #26 | #29 | Blocked |
| 28 | Implement remove / archive member with PII anonymization | MED | #26, #27 | #79 | Blocked |
| 29 | Build audit log writer utility + read endpoint (BR-13) | HIGH | — | — | Ready to start |
| 30 | Implement member profile CRUD | MED | #25 | #31 | Blocked |
| 31 | Implement instrument list management (default + custom) | MED | #30 | #40 | Blocked |
| 32 | Write API auth-matrix tests for Sprint 0–1 routes | HIGH | #24, #25, #26, #27, #28, #29, #30, #31 | — | Blocked |
| 33 | Write RLS bypass tests for Sprint 0–1 tables | HIGH | #24 | #79 | Blocked |

# Sprint 2 — Scheduling Core

Availability, service weeks, invitations, conflicts

Legend:    Box = feature issue   |   Note shape = chore issue (tests, infra, audits)   |   Red fill = priority:high   Orange fill = priority:med   Green fill = priority:low   |   Grey dashed box = closed Sprint 0 prerequisite (already satisfied)

## Sprint 2 — Scheduling Core — Issue Detail

| # | Title | Priority | Blocked by (open) | Blocks | Status |
| --- | --- | --- | --- | --- | --- |
| 34 | Implement availability set/get | HIGH | #30 | #35, #36, #46 | Blocked |
| 35 | Implement availability delete-to-unset with conflict trigger (BR-15) | HIGH | #34 | #46 | Blocked |
| 36 | Build team availability grid endpoint | MED | #34 | #48 | Blocked |
| 37 | Implement service week CRUD | HIGH | — | #38, #39, #40, #54, #59 | Ready to start |
| 38 | Implement service week hard-delete (BR-16) | MED | #37 | — | Blocked |
| 39 | Implement service week cancel/reactivate (BR-17) | MED | #37 | #62 | Blocked |
| 40 | Implement send set invitation (BR-05 double-booking check) | HIGH | #37, #29 | #41, #42, #43, #44, #45 | Blocked |
| 41 | Implement accept invitation flow | HIGH | #40 | #49 | Blocked |
| 42 | Implement deny invitation with reason (BR-08 denial cap) | HIGH | #40 | #49 | Blocked |
| 43 | Implement withdraw invitation | MED | #40 | — | Blocked |
| 44 | Implement token-based public invitation lookup | HIGH | #40 | #49 | Blocked |
| 45 | Build 24-hour dual-party reminder scheduler | HIGH | #40 | #51 | Blocked |
| 46 | Implement conflict detection on availability change | HIGH | #34, #35, #41 | #47, #50 | Blocked |
| 47 | Implement conflict resolution flow (3 paths) | HIGH | #46 | #50 | Blocked |
| 48 | Build Week View screen (Admin / Set Leader) | HIGH | #36, #40, #47 | — | Blocked |
| 49 | Build Invitation Response screen (mobile, no-login) | HIGH | #41, #42, #44 | — | Blocked |
| 50 | Build Conflict Resolution screen | MED | #47 | — | Blocked |
| 51 | Write invitation state machine unit tests | HIGH | #40, #41, #42, #43 | #52 | Blocked |
| 52 | Write E2E tests for invitation & conflict flows | HIGH | #48, #49, #50, #51 | — | Blocked |

# Sprint 3 — Setlists & Calendar

Songs, setlists, events, Google Calendar sync

Legend:    Box = feature issue   |   Note shape = chore issue (tests, infra, audits)   |   Red fill = priority:high   Orange fill = priority:med   Green fill = priority:low   |   Grey dashed box = closed Sprint 0 prerequisite (already satisfied)

## Sprint 3 — Setlists & Calendar — Issue Detail

| # | Title | Priority | Blocked by (open) | Blocks | Status |
| --- | --- | --- | --- | --- | --- |
| 53 | Implement song catalog CRUD + search (BR-09 key validation) | HIGH | — | #55, #57, #58 | Ready to start |
| 54 | Implement draft setlist creation (BR-01 zero-song valid state) | HIGH | #37 | #55, #56 | Blocked |
| 55 | Implement add/remove/reorder setlist songs (BR-07 no duplicates) | HIGH | #54, #53 | #56, #64 | Blocked |
| 56 | Implement publish setlist (BR-01 zero-song publish) | HIGH | #55 | #64, #66 | Blocked |
| 57 | Implement per-song key override validation (BR-09) | MED | #53, #55 | — | Blocked |
| 58 | Implement song-level document attachment (signed URLs) | MED | #53 | — | Blocked |
| 59 | Implement event CRUD (BR-10 time validation) | HIGH | #37 | #60, #62, #63 | Blocked |
| 60 | Implement event attendee assignment | MED | #59, #41 | #62 | Blocked |
| 61 | Implement Google Calendar OAuth connect/disconnect | HIGH | — | #62 | Ready to start |
| 62 | Implement Google Calendar event sync (create/update/delete + graceful degradation) | HIGH | #59, #60, #61 | #66 | Blocked |
| 63 | Implement iCal (.ics) export fallback | LOW | #59 | — | Blocked |
| 64 | Build Setlist Builder screen | HIGH | #55, #56, #57 | #66 | Blocked |
| 65 | Build Member Week View screen | MED | #56, #59, #58 | — | Blocked |
| 66 | Write E2E tests for setlist & calendar flows | HIGH | #56, #62, #64, #65 | — | Blocked |

# Sprint 4 — Notifications, Guests & Launch

Notifications, guest flow, security hardening, deploy gate

Legend:    Box = feature issue   |   Note shape = chore issue (tests, infra, audits)   |   Red fill = priority:high   Orange fill = priority:med   Green fill = priority:low   |   Grey dashed box = closed Sprint 0 prerequisite (already satisfied)

## Sprint 4 — Notifications, Guests & Launch — Issue Detail

| # | Title | Priority | Blocked by (open) | Blocks | Status |
| --- | --- | --- | --- | --- | --- |
| 67 | Integrate Pingram SMS dispatch + webhook verification | HIGH | — | #69, #72 | Ready to start |
| 68 | Integrate Resend email dispatch + webhook verification | HIGH | — | #69, #72 | Ready to start |
| 69 | Wire notification trigger logic for all Phase 1 event types | HIGH | #67, #68, #40, #47, #56, #59, #62 | #71, #82 | Blocked |
| 70 | Implement notification preferences (BR-14 minimum-channel guard) | HIGH | — | #69 | Ready to start |
| 71 | Implement in-app notification inbox endpoints | HIGH | #69 | #73 | Blocked |
| 72 | Implement guest invitation flow (existing vs. new user) | HIGH | #40, #41, #42 | — | Blocked |
| 73 | Build Notification Inbox screen | MED | #71 | — | Blocked |
| 74 | Build Admin Global Dashboard screen | MED | #37, #40, #47, #39 | — | Blocked |
| 75 | Implement PWA manifest & install prompt | MED | — | — | Ready to start |
| 76 | Implement rate limiting on auth, SMS, and write endpoints | HIGH | — | #81 | Ready to start |
| 77 | Audit input validation (Zod) across all Phase 1 routes | HIGH | — | #80, #79 | Ready to start |
| 78 | Run infrastructure security pass (HTTPS, CSP, secret scan) | HIGH | — | #79 | Ready to start |
| 79 | Conduct manual OWASP Top 10 review | HIGH | #76, #77, #78 | #83 | Blocked |
| 80 | Run full auth-bypass & RLS-bypass test suite (all Phase 1 tables) | HIGH | #76, #77 | #79, #83 | Blocked |
| 81 | Run performance/load test pass against staging | MED | #76 | #83 | Blocked |
| 82 | Run full E2E regression pass across all Phase 1 critical paths | HIGH | #52, #66, #71, #72 | #83 | Blocked |
| 83 | Set up production deploy gate & rollback plan | HIGH | #79, #80, #81, #82 | — | Blocked |

# Appendix — Full Open Issue List (All Sprints)

All 60 open issues, #24–#83, sorted by issue number.

| # | Title | Priority | Blocked by (open) | Blocks | Status |
| --- | --- | --- | --- | --- | --- |
| 24 | Implement church group creation | HIGH | — | #25, #26 | Ready to start |
| 25 | Implement join church group via invite code | HIGH | #24 | #30, #26 | Blocked |
| 26 | Build member directory endpoint | MED | #24 | #27, #28 | Blocked |
| 27 | Implement role assignment & multi-admin support (BR-03, BR-04, BR-12) | HIGH | #26 | #29 | Blocked |
| 28 | Implement remove / archive member with PII anonymization | MED | #26, #27 | #79 | Blocked |
| 29 | Build audit log writer utility + read endpoint (BR-13) | HIGH | — | — | Ready to start |
| 30 | Implement member profile CRUD | MED | #25 | #31 | Blocked |
| 31 | Implement instrument list management (default + custom) | MED | #30 | #40 | Blocked |
| 32 | Write API auth-matrix tests for Sprint 0–1 routes | HIGH | #24, #25, #26, #27, #28, #29, #30, #31 | — | Blocked |
| 33 | Write RLS bypass tests for Sprint 0–1 tables | HIGH | #24 | #79 | Blocked |
| 34 | Implement availability set/get | HIGH | #30 | #35, #36, #46 | Blocked |
| 35 | Implement availability delete-to-unset with conflict trigger (BR-15) | HIGH | #34 | #46 | Blocked |
| 36 | Build team availability grid endpoint | MED | #34 | #48 | Blocked |
| 37 | Implement service week CRUD | HIGH | — | #38, #39, #40, #54, #59 | Ready to start |
| 38 | Implement service week hard-delete (BR-16) | MED | #37 | — | Blocked |
| 39 | Implement service week cancel/reactivate (BR-17) | MED | #37 | #62 | Blocked |
| 40 | Implement send set invitation (BR-05 double-booking check) | HIGH | #37, #29 | #41, #42, #43, #44, #45 | Blocked |
| 41 | Implement accept invitation flow | HIGH | #40 | #49 | Blocked |
| 42 | Implement deny invitation with reason (BR-08 denial cap) | HIGH | #40 | #49 | Blocked |
| 43 | Implement withdraw invitation | MED | #40 | — | Blocked |
| 44 | Implement token-based public invitation lookup | HIGH | #40 | #49 | Blocked |
| 45 | Build 24-hour dual-party reminder scheduler | HIGH | #40 | #51 | Blocked |
| 46 | Implement conflict detection on availability change | HIGH | #34, #35, #41 | #47, #50 | Blocked |
| 47 | Implement conflict resolution flow (3 paths) | HIGH | #46 | #50 | Blocked |
| 48 | Build Week View screen (Admin / Set Leader) | HIGH | #36, #40, #47 | — | Blocked |
| 49 | Build Invitation Response screen (mobile, no-login) | HIGH | #41, #42, #44 | — | Blocked |
| 50 | Build Conflict Resolution screen | MED | #47 | — | Blocked |
| 51 | Write invitation state machine unit tests | HIGH | #40, #41, #42, #43 | #52 | Blocked |
| 52 | Write E2E tests for invitation & conflict flows | HIGH | #48, #49, #50, #51 | — | Blocked |
| 53 | Implement song catalog CRUD + search (BR-09 key validation) | HIGH | — | #55, #57, #58 | Ready to start |
| 54 | Implement draft setlist creation (BR-01 zero-song valid state) | HIGH | #37 | #55, #56 | Blocked |
| 55 | Implement add/remove/reorder setlist songs (BR-07 no duplicates) | HIGH | #54, #53 | #56, #64 | Blocked |
| 56 | Implement publish setlist (BR-01 zero-song publish) | HIGH | #55 | #64, #66 | Blocked |
| 57 | Implement per-song key override validation (BR-09) | MED | #53, #55 | — | Blocked |
| 58 | Implement song-level document attachment (signed URLs) | MED | #53 | — | Blocked |
| 59 | Implement event CRUD (BR-10 time validation) | HIGH | #37 | #60, #62, #63 | Blocked |
| 60 | Implement event attendee assignment | MED | #59, #41 | #62 | Blocked |
| 61 | Implement Google Calendar OAuth connect/disconnect | HIGH | — | #62 | Ready to start |
| 62 | Implement Google Calendar event sync (create/update/delete + graceful degradation) | HIGH | #59, #60, #61 | #66 | Blocked |
| 63 | Implement iCal (.ics) export fallback | LOW | #59 | — | Blocked |
| 64 | Build Setlist Builder screen | HIGH | #55, #56, #57 | #66 | Blocked |
| 65 | Build Member Week View screen | MED | #56, #59, #58 | — | Blocked |
| 66 | Write E2E tests for setlist & calendar flows | HIGH | #56, #62, #64, #65 | — | Blocked |
| 67 | Integrate Pingram SMS dispatch + webhook verification | HIGH | — | #69, #72 | Ready to start |
| 68 | Integrate Resend email dispatch + webhook verification | HIGH | — | #69, #72 | Ready to start |
| 69 | Wire notification trigger logic for all Phase 1 event types | HIGH | #67, #68, #40, #47, #56, #59, #62 | #71, #82 | Blocked |
| 70 | Implement notification preferences (BR-14 minimum-channel guard) | HIGH | — | #69 | Ready to start |
| 71 | Implement in-app notification inbox endpoints | HIGH | #69 | #73 | Blocked |
| 72 | Implement guest invitation flow (existing vs. new user) | HIGH | #40, #41, #42 | — | Blocked |
| 73 | Build Notification Inbox screen | MED | #71 | — | Blocked |
| 74 | Build Admin Global Dashboard screen | MED | #37, #40, #47, #39 | — | Blocked |
| 75 | Implement PWA manifest & install prompt | MED | — | — | Ready to start |
| 76 | Implement rate limiting on auth, SMS, and write endpoints | HIGH | — | #81 | Ready to start |
| 77 | Audit input validation (Zod) across all Phase 1 routes | HIGH | — | #80, #79 | Ready to start |
| 78 | Run infrastructure security pass (HTTPS, CSP, secret scan) | HIGH | — | #79 | Ready to start |
| 79 | Conduct manual OWASP Top 10 review | HIGH | #76, #77, #78 | #83 | Blocked |
| 80 | Run full auth-bypass & RLS-bypass test suite (all Phase 1 tables) | HIGH | #76, #77 | #79, #83 | Blocked |
| 81 | Run performance/load test pass against staging | MED | #76 | #83 | Blocked |
| 82 | Run full E2E regression pass across all Phase 1 critical paths | HIGH | #52, #66, #71, #72 | #83 | Blocked |
| 83 | Set up production deploy gate & rollback plan | HIGH | #79, #80, #81, #82 | — | Blocked |